## Sheet1
Question Text | Question Type | Option 1 | Option 2 | Option 3 | Option 4 | Correct Answer | Time in seconds
A project manager is trying to reduce the project duration without changing the project scope. She decides to overlap design and construction phases to accelerate completion. Which scheduling technique is she using? | Multiple Choice | A. Crashing | B. Fast tracking | C. Resource leveling | D. Precedence diagramming | B. Fast tracking | 30 | 2
A construction project has fallen behind schedule. The project manager wants to allocate more workers to critical path activities to make up for lost time. Which technique is she applying? | Multiple Choice | A. Fast tracking | B. Lead and lag adjustment | C. Crashing | D. Resource smoothing | C. Crashing | 30 | 3
During a project update meeting, the team realizes that several activities have started but are not progressing as fast as expected. Which project tool should the manager use to identify how much the delay might impact the project completion date? | Multiple Choice | A. Gantt Chart | B. Critical Path Method | C. Earned Value Analysis | D. Milestone list | B. Critical Path Method | 30 | 2
The project sponsor wants to know how the schedule will be impacted if one of the key resources becomes unavailable for a week. What type of analysis would provide this information? | Multiple Choice | A. Trend analysis | B. Resource leveling | C. What-if scenario analysis | D. Parametric estimation | C. What-if scenario analysis | 30 | 3
A project manager is implementing a just-in-time delivery method, where tasks are started as resources become available, without relying on a pre-established schedule. Which scheduling approach is she using? | Multiple Choice | A. Rolling wave planning | B. On-demand scheduling | C. Iterative scheduling | D. Crashing | B. On-demand scheduling | 30 | 2
A project team is using a combination of agile methods and traditional waterfall approaches for different parts of the project. Which term best describes this scheduling approach? | Multiple Choice | A. Hybrid methodology | B. Crashing | C. Iterative scheduling | D. Lead and lag management | A. Hybrid methodology | 30 | 1
A project team member asks why they are starting construction before all architectural plans are completed. The project manager explains that certain parts can begin while other sections are still in the design phase. What type of relationship between activities is this? | Multiple Choice | A. Finish-to-Start | B. Start-to-Start | C. Finish-to-Finish | D. Start-to-Finish | B. Start-to-Start | 30 | 2
A software project is experiencing delays, and the project manager uses earned value analysis to calculate the schedule performance index (SPI). The SPI is 0.85. What does this indicate? | Multiple Choice | A. The project is ahead of schedule. | B. The project is behind schedule. | C. The project is within acceptable time limits. | D. The project schedule requires no changes. | B. The project is behind schedule. | 30 | 2
A project manager needs to ensure that a specific task is completed 10 days before another can begin. This requirement introduces a time gap between activities. What scheduling adjustment is needed? | Multiple Choice | A. Lead | B. Lag | C. Fast tracking | D. Crashing | B. Lag | 30 | 2
The project team estimates a task will take 4 weeks in the worst case, 2 weeks in the best case, and 3 weeks most likely. What duration estimate should the project manager use based on the three-point estimating formula? | Multiple Choice | A. 2.5 weeks | B. 3 weeks | C. 3.5 weeks | D. 4 weeks | C. 3.5 weeks | 30 | 3
A project manager realizes that several tasks are using more resources than planned, and the project is at risk of running over budget. Which analysis technique should the project manager use to evaluate the financial impact of this situation? | Multiple Choice | A. Earned Value Analysis | B. Critical Path Analysis | C. Root Cause Analysis | D. Resource Leveling | A. Earned Value Analysis | 30 | 1
The client has requested a significant change to the project scope, and the project manager needs to assess how this will affect the schedule. What should the project manager do first? | Multiple Choice | A. Update the resource management plan | B. Submit a change request | C. Review the schedule baseline | D. Reassign project team members | C. Review the schedule baseline | 30 | 3
A software development project is using agile methodologies. Every two weeks, the team delivers a working product increment and reviews progress. What is this two-week cycle called? | Multiple Choice | A. Iteration | B. Milestone | C. Phase | D. Deliverable | A. Iteration | 30 | 1
The project manager wants to accelerate the project timeline without adding more resources. She suggests executing some tasks in parallel, although they were originally planned to be performed sequentially. What technique is she using? | Multiple Choice | A. Critical Chain | B. Crashing | C. Fast Tracking | D. Rolling Wave Planning | C. Fast Tracking | 30 | 3
During project execution, a team member reports that an external vendor is delaying a critical task. This is considered an external dependency. How should the project manager address this situation? | Multiple Choice | A. Update the milestone list | B. Issue a change request | C. Adjust the resource calendar | D. Contact the vendor and apply pressure | D. Contact the vendor and apply pressure | 30 | 4
The project manager is using a network diagram to display all tasks, dependencies, and the critical path. She notices that one task has a large amount of float. What does this indicate? | Multiple Choice | A. The task can be delayed without affecting the project completion date | B. The task has the longest duration in the project | C. The task is a critical path activity | D. The task requires additional resources | A. The task can be delayed without affecting the project completion date | 30 | 1
A project manager calculates that the project has a total float of 10 days. What does this mean? | Multiple Choice | A. The project can be delayed by 10 days without missing the final deadline | B. The project is ahead of schedule by 10 days | C. A specific activity can be delayed by 10 days without affecting the project finish date | D. The project sponsor has 10 extra days for approval processes | C. A specific activity can be delayed by 10 days without affecting the project finish date | 30 | 3
While managing a construction project, the project manager sees that a particular task will take much longer due to unexpected regulatory approvals. Which action should the manager take to minimize the impact on the overall project schedule? | Multiple Choice | A. Use the critical path method to reanalyze the project timeline | B. Apply resource smoothing | C. Compress the schedule using crashing | D. Increase the task's float time | A. Use the critical path method to reanalyze the project timeline | 30 | 1
A project is moving smoothly until a team member falls ill and cannot complete their assigned tasks on time. This task is on the critical path. What is the most likely outcome if no adjustments are made? | Multiple Choice | A. The project cost will increase | B. The project finish date will be delayed | C. The scope of the project will change | D. The task will have additional float | B. The project finish date will be delayed | 30 | 2
A project manager is working on a schedule using rolling wave planning. What does this imply? | Multiple Choice | A. The project schedule is fixed and not subject to changes | B. Detailed planning is done only for the near-term activities, while future activities are planned at a high level | C. All project phases are planned simultaneously | D. The schedule is based on fixed durations for all tasks | B. Detailed planning is done only for the near-term activities, while future activities are planned at a high level | 30 | 2
A project manager is trying to reduce the project duration without changing the project scope. She decides to overlap design and construction phases to accelerate completion. Which scheduling technique is she using? | Multiple Choice | A. Crashing | B. Fast tracking | C. Resource leveling | D. Precedence diagramming | B. Fast tracking | 30 | 2
A construction project has fallen behind schedule. The project manager wants to allocate more workers to critical path activities to make up for lost time. Which technique is she applying? | Multiple Choice | A. Fast tracking | B. Lead and lag adjustment | C. Crashing | D. Resource smoothing | C. Crashing | 30 | 3
During a project update meeting, the team realizes that several activities have started but are not progressing as fast as expected. Which project tool should the manager use to identify how much the delay might impact the project completion date? | Multiple Choice | A. Gantt Chart | B. Critical Path Method | C. Earned Value Analysis | D. Milestone list | B. Critical Path Method | 30 | 2
The project sponsor wants to know how the schedule will be impacted if one of the key resources becomes unavailable for a week. What type of analysis would provide this information? | Multiple Choice | A. Trend analysis | B. Resource leveling | C. What-if scenario analysis | D. Parametric estimation | C. What-if scenario analysis | 30 | 3
A project manager is implementing a just-in-time delivery method, where tasks are started as resources become available, without relying on a pre-established schedule. Which scheduling approach is she using? | Multiple Choice | A. Rolling wave planning | B. On-demand scheduling | C. Iterative scheduling | D. Crashing | B. On-demand scheduling | 30 | 2
A project team is using a combination of agile methods and traditional waterfall approaches for different parts of the project. Which term best describes this scheduling approach? | Multiple Choice | A. Hybrid methodology | B. Crashing | C. Iterative scheduling | D. Lead and lag management | A. Hybrid methodology | 30 | 1
A project team member asks why they are starting construction before all architectural plans are completed. The project manager explains that certain parts can begin while other sections are still in the design phase. What type of relationship between activities is this? | Multiple Choice | A. Finish-to-Start | B. Start-to-Start | C. Finish-to-Finish | D. Start-to-Finish | B. Start-to-Start | 30 | 2
A software project is experiencing delays, and the project manager uses earned value analysis to calculate the schedule performance index (SPI). The SPI is 0.85. What does this indicate? | Multiple Choice | A. The project is ahead of schedule. | B. The project is behind schedule. | C. The project is within acceptable time limits. | D. The project schedule requires no changes. | B. The project is behind schedule. | 30 | 2
A project manager needs to ensure that a specific task is completed 10 days before another can begin. This requirement introduces a time gap between activities. What scheduling adjustment is needed? | Multiple Choice | A. Lead | B. Lag | C. Fast tracking | D. Crashing | B. Lag | 30 | 2
The project team estimates a task will take 4 weeks in the worst case, 2 weeks in the best case, and 3 weeks most likely. What duration estimate should the project manager use based on the three-point estimating formula? | Multiple Choice | A. 2.5 weeks | B. 3 weeks | C. 3.5 weeks | D. 4 weeks | C. 3.5 weeks | 30 | 3